# Committee Board Member Meeting Agenda July 22nd 2025

## Action Points from June CBM (checking them off if done and if not re-allocating):
Done
In Progress
Outstanding

- Gaetano: Create workflow handover documentation for technical systems and operations → had meeting with Ruben – shared handover doc – Ruben to feedback about doc (from Ruben?) – Action Isobel will chase Ruben
- ISO + SJ: Also work on handover documentation for their roles - outstanding
- Colin: Research environmental liability insurance requirements for the organization- in progress – other liability insurance already renewed
- Colin: Write up risk analysis meeting notes and documentation – outstanding
- Howie and Iso: have written up risk assessment doc https://members.circularrevolution.org/f/5583
- Iso: Review agreements made with riders and volunteers, ensure they're updated for anyone with >1 year involvement – action Iso
- Determine whether caddy contents are classified as biohazardous or offensive waste material: Classified as Biohazardous
- Howie: Model business growth scenarios to determine capacity and financial tipping points.
- Documentation added to the website (WooCommerce) explaining the payment model
- Find volunteers with coding skills to support technical operations and review workflow documentation: Ruben found

## Main Agenda: Develop a partnership plan with Canal & River Trust
- Update on discussions so far: Not much conversation so far – they fed back that our involvement could help with their targets.
- What do we want? Building and running a (community/boater led) composting facility (mainly in the outside area- which we would make secure to the general public) and having use of storage, electricity and water for the general running of our operations, in return for something between these points:
  a.
  take over the entire general running and maintenance of the facility inc. elsan and water point, maintaining the bin lock up, whilst also

  ...and..
  b.
  Facility caretaking role - first port of call for security / reporting issues/wear and tear re. the elsan point, water point and bin lock up area.
- Discuss planning for a meeting with CRT
  - who’s attending? Isobel and Lou
  - What leverage do we have?:
    - Can save them money in the long term, and work toward a self-sustaining boater run facility
    - Working business model
    - Experience of running compost drop-off facility (Stabbots)
    - working volunteer program
    - Community support
    - PR opportunities (including our partners)
  - We need the following, so we can come back to them with a proposal:
    - running schedule and costs
    - any site restrictions
## AOB:
  - Sept. meeting open to all members/wider community: Agenda to include: Finance update from Howie to present finance update. Update from Stanstead Drop Off, Hopefully update from CRT meeting!
    - Action – Colin: large poll for maximum attendance (will the meeting be online or in person?)
  - Email from a research person who works with Old Tree Soil – lewes – including suggestions about how we can all work together – exciting!

## New Actions
- Colin: Poll next meeting
- Lou Isobel: CRT meeting
- Isobel: check in with
- Howie: prepare a finance/modelling update for the september CBM Meeting